## Installation Checklist
Step | Task Description | Additional Tooling | Tool Status | Materials / Consumables | Estimated Qty | Status | Responsible | Note
1 — FOOT PLATES | [8 empty] | 3
1.1 | Mark installation layout on site based on floorplan | Laser line, String / string line, Chalk, | Packed | — | — | — | — | — | 1
1.2 | Position and install footplates for main body | Concrete drill, 16mm Concrete drill bit, Battery drill, Impact driver | Packed | M16 × 100mm Screw Bolt | 40 | Order From Macsim | — | — | 2
1.3 | Mark footplate location for exchange table but don’t install yet | — | — | Foot Plates | x20 | Rikky to Cut | — | — | 1
1.4 | Place main body on footplates ensuring 120mm height between floor and frame body for slag collection trays | Large spanners, Overhead gantry / Firana hoist | Packed, Firana meet on site | — | — | — | — | — | 2
1.5 | Connect exchange table body with threaded rod and placed on roller wheels for access to chain drive motor installation. Foot plates installed and welded after chain tensioned. | Roller wheels x4, Lifting Equipment, Crowbar, Long Prybar | Packed | Threaded Rod m16 | 2m | Packed | — | — | 1
1.6 | Bed machined surfaces will require deburring and cleaning and potentialy threads retapped | Deburr knife, Wet Stone, Angle grinder, Scotchbright,Files, Taps (M5 & M6), Drill bit selection | Need Sanding Pads + backing, Rags, scotchbright | 870 grit sanding pad and backing, Slideway oil, WD-40, Cotton rags | — | To Source | — | — | 2
1.7 | Level machine using laser level and reciever then machinist level to 0.2mm/m | Machinist Levels, Laser level with tripod & receiver | Packed; Potentially Hire Tripod | — | — | — | — | — | 1
1.8 | Rack Alignment.Use free linear bearing & mag base dial gauge to run along rack to ensure straightness. - when unpackaging racks be careful not to remove lettering hints as the racks have been drilled in place and have designated location on machine base. | Flat edge/Bubble Level, Mag Base Dial Guage, Torque wrench, | Packed | — | — | — | — | — | 2
1.9 | Weld feet to footplates once machine is confirmed level | Welder | Site to Provide | Welding rods | — | Packed | — | — | 1
| 2 — CHAIN & TABLE INSTALL | [7 empty] | 3
2.1 | Install chain, chain drive motor, and chain clips | Deadblow hammer, Standard hammer, Allen key set, Socket set with extensions & swivel joints, Lifting straps and shackles | Packed | Slideway oil, Anti-seize compound | — | packed | — | — | 1
2.2 | Install exchange table frame WITHOUT slats, allows chain tension to be set | — | — | — | — | — | — | — | 2
2.3 | Push exchange table frame toward main body for footplate installation | — | — | — | — | — | — | — | 1
2.4 | Install and weld exchange table frame footplates after leveling | — | — | — | — | — | — | — | 2
2.5 | Align exchange tables adjustable rollers with string line - Forklift required | Forklift (lifting boom attachment preferred) | Site to Provide | — | — | Potentially have Boom? | — | — | 1
3 — LINEAR RAILS & CROSS BEAM | [8 empty] | 3
3.1 | Deburr and clean underside of crossbeam gantry and all linear bearing surfaces before assembly | — | — | NA | — | — | — | — | 1
3.2 | Connect and route oil lines for linear bearings tidily before placing crossbeam | — | — | — | — | — | — | — | 2
3.3 | Place crossbeam onto linear bearings and Install crossbeam mounting bolts (Finger Tight) | — | — | — | — | — | — | — | 1
3.4 | Position sturdy table in centre of machine and level using packers and mount dial gauge to laser head mounting screw holes via adapter bolt | Sturdy table (Find on Site), Packers, Engineer's square, Clamps, Adapter bolt | Packed, Adapter bolt to be made | — | — | — | — | — | 2
3.5 | Manually move crossbeam along Y axis to align with square, clamp crossbeam in position | — | — | — | — | — | — | — | 1
3.6 | Push gantry along X axis and tap crossbeam with deadblow for target ≤0.2mm/m on both X and Y axes. record dial gauge readings. Note: Can complete cable installation and required electrics first, then return to squaring | — | — | — | — | — | — | — | 2
3.7 | Tighten crossbeam mounting bolts to suitable torque spec once squared, recheck after tightening, and verify square at another location on machine | — | — | — | — | — | — | — | 1
3.8 | Verify squareness at a second location on the machine, record result | — | — | — | — | — | — | — | 2
4 — MOTORS & DRIVE GEAR | [8 empty] | 3
4.1 | Install Y axis motor — mount bolts finger-tight initially | — | — | Included in kit | — | — | — | — | 1
4.2 | Push drive gear into racks until fully seated with zero play | — | — | — | — | — | — | — | 2
4.3 | Tighten motor mounting bolts 30° past hand-tight | — | — | — | — | — | — | — | 1
4.4 | Tighten tension bolts to apply preload on driving gear | — | — | — | — | — | — | — | 2
5 — CABLE TRACKS AND BODY PANELS | [8 empty] | 3
5.1 | Install front body for valve island connections (Extraction Doors), Side cable trays, oil reservoir, Gas Regulators. Note: Probably ideal to run electrical and gas lines now if ready | — | — | Gas fittings, Gas hoses, Sealant / thread lock | Gas Fittings + Gas hoses TBC | Source near site. | — | — | 1
5.2 | Install front panels and rear pillars with mounting bolts Fingertight only (allows adjustment during wall panel install) | — | — | Large cardboard roll or plywood for panel protection | — | — | — | — | 2
5.3 | Install side wall framing then remove assembly together to lay flat on wall panels for modifications to alignment holes | — |  | clear working area required | — | Process dependant on site | — | — | 1
5.4 | Remove centre wall panels to access wall frame mounting bolt holes before lifting wall sections into position using forklift or manpower. Align and adjust front and back pillars as necessary then tighten all body mounting bolts | — | — | — | — | — | — | — | 2
6 — WINDOW INSTALL | [8 empty] | 3
6.1 | Retap aluminium window strips at larger diameter since manufacturing quality is low, Drill clearance holes in machine wall panels. | — | — | Loctite (thread lock), M5 ss Bolts 10mm | — | Packed | — | — | 1
6.2 | Loosely install bottom aluminium rail, Seat window glass in bottom rail using suction cups, push top rail into position while second installer tightens rails to hold glass in place | Window suction cups x2 | Packed | — | — | — | — | — | 2
ROOF INSTALL | [8 empty] | 3
7.1 | Install roof panels | Ladder | Find on Site | Included in kit | — | — | — | — | 1
LIGHT CURTAINS / RUBBER CURTAINS | [8 empty] | 3
8.1 | Confirm light curtain and rubber curtain requirements with customer | — | — | M6/M8 masonry screw bolts | 12–16 off | — | — | — | 1
8.2 | Design for manufacture based on customer requirements, Mark and drill mounting holes in floor for light curtains after ensuring alignment | — | — | Light curtain bollard (if required), | — | — | — | — | 2
8.3 | Drill and tap machine frame to install threaded rod and clamping plate for securing rubber curtain as required | Hole punches | — | Additional rubber curtain material (if required), threaded rod 6mm, Clamping Plates | — | — | — | — | 1
EXTRACTION AND DUCTING | [8 empty] | 3
9.1 | PREFERRED: Source 200mm dia metal ducting and make drawinf for fabrication + connecting flanges to suit | — | — | 200mm dia metal ducting | — | — | — | — | 1
9.2 | ALTERNATIVE: Use 350mm dia plastic ducting attached with 2x per end hose clamps | — | — | 350mm hose clamps | 4 off | — | — | — | 2
9.3 | Install and connect ducting to extraction port | — | — | — | — | — | — | — | 1
9.4 | Ensure 3 phase power into extractor separate draw from voltage regulator. | — | — | — | — | — | — | — | 2
CABLE PROTECTION AND WALL MOUNTING | [8 empty] | 3
10.1 | After machine and all auxiliaries are in final position, draw for fabrication cable covers | — | — | Floor cable covers (custom fabricated) | — | TBC | — | — | 1
10.2 | wall-mount required cables with conduit and saddle clamps | — | — | Saddle clamps, | As req. | Some in stock, Source on site | — | — | 2
WATER CHILLER | [8 empty] | 3
11.1 | Position water chiller unit | — | — | — | — | — | — | — | 1
11.2 | Connect coolant water lines to laser source and chiller | — | — | — | — | — | — | — | 2
11.3 | Commission and pressure-test chiller circuit | — | — | — | — | — | — | — | 1
11.4 | Ensure Clean, and full with clean distilled water | — | — | Distilled Water | 40L | Source on Site | — | — | 2
VOLTAGE REGULATOR | [8 empty] | 3
12.1 | Position voltage regulator unit | — | — | — | — | — | — | — | 1
12.2 | Connect input supply and output to machine cabinet | — | — | — | — | — | — | — | 2
12.3 | Verify output voltage within machine specification before power-on | — | — | — | — | — | — | — | 1
CONTROL CABINET AND SYSTEMS | [8 empty] | 3
13.1 | Position and secure control cabinet | — | — | — | — | — | — | — | 1
13.2 | Route and connect all control wiring | — | — | — | — | — | — | — | 2
13.3 | Commission control system; test all axes, limits, and safety functions | — | — | — | — | — | — | — | 1
AIR COMPRESSOR | [8 empty] | 3
14.1 | Position air compressor or tie into customers existing lines | — | — | — | — | — | — | — | 1
14.2 | Connect compressed air supply lines to machine | — | — | — | — | — | — | — | 2
14.3 | Set and verify operating pressure to machine specification | — | — | — | — | — | — | — | 1
14.4 | Test all pneumatic functions on machine | — | — | — | — | — | — | — | 2

## Tools
PRE-JOB PACK LIST — 4020GA Body Installation
TOOLING
Tool / Equipment | Have it? ✓/✗ | Location (van / workshop / hire) | Notes
Laser line | Packed | Work Van | Missing Mag Base
String / string line | Packed | Sean Tools
Concrete drill | Packed | Work Van
16mm concrete drill bit | Packed | Work Van
Battery drill | Packed | Work Van
Impact driver | Packed | Aaron Tools
Socket set (with extensions & swivel joints) | Packed | Aaron Tools
Overhead gantry / Firana hoist | Hire | —
Large spanners | Packed | Work Van
Stick welder | Site Supplied | —
Roller wheels ×4 | Packed | Work Van
Lifting equipment (forklift / hoist) | Site Supplied | —
Large pry bar | Packed | Work Van
Crowbar | No | Grey Van
Laser level with tripod & receiver | Hire | —
Bubble level | Packed | Work Van
Deburr stone | Packed | Work Van
Files (assorted) | Packed | Aaron Tools
Torque wrench | No | —
Long level / straight edge | Packed | Work Van
Scouring pads | No | —
Dial gauge with mag base | Packed | Work Van
Angle grinder with fine sanding disc | No | —
Deburr knives | Packed | Aaron Tools
Taps — M5 & M6 | Packed | Aaron Tools + Workshop Tools, Work Van
Drill bit selection (general) | Packed | Aaron Tools + Workshop Tools, Work Van
Deadblow hammer | Packed | Aaron Tools
Standard hammer | Packed | Aaron Tools
Forklift with lifting boom attachment | TBC | — | Confirm availability on site
Allen key set (full) | Packed | Sean/Aaron Tools
Lifting straps and shackles | Packed | Work Van | Check SWL rating before use
Rags (clean) | No | —
Sturdy table (for squaring) | Site Supplied | —
Packers / shims | Packed | Work Van
Adapter bolt (laser head mounting thread) | No | — | Confirm thread spec before job
Engineer's square (large) | Packed | Work Van
Clamps (assorted) | Packed | Work Van
Electrical toolkit | Packed | Work Van
Window suction cups | Packed | Work Van
Ladder | Site Supplied | —
Hole punches | Packed | Work Van | If light curtains required
Rolling Sopport for crossbeams of echange table

## Materials
PRE-JOB PACK LIST — 4020GA Body Installation
MATERIALS & CONSUMABLES
Item | Qty Required | Qty in Stock | Order Required? | Supplier / Notes
M16 × 100mm Screw Bolt | 40 | 4 | x40
Foot Plates | 20 | 0 | x20
Welding rods | As req. | Plenty | —
M16 Threaded Rod (2m lengths, cut to 0.5m) | 4 off | Enough | —
Slideway oil | As req. | Plenty | —
WD-40 | As req. | Enough | —
Cotton rags | As req. | Minimal | 2 bags - get full cotton | Most rags are wasted. Get quality checked cotton rags
Anti-seize compound | As req. | Enough | —
Loctite thread lock | As req. | Enough | —
Gas fittings | TBC — confirm before job | Find near site/find past purchases | TBC | Clarify spec with customers site
Gas hoses | TBC — confirm before job | Bulk order hoses | Dependant on customer site | Clarify spec with customers site
Sealant / thread lock for gas | As req. | Another 58-11, locktite 55 wanted | 1x Loxeal 58-11
Large cardboard roll OR plywood sheets (panel protection) | As req. | Enough | — | For protecting wall panels laid on ground
M6/M8 masonry screw bolts | 12–16 off | None | TBC | For light curtains (if required)
350mm hose clamps | 4 off | None | 4x 350dia hose clamps | If plastic ducting used
200mm dia metal ducting | TBC | For Fab if Confirmed | TBC | Preferred option for extraction
Saddle clamps | As req. | Find near site | —
Floor cable covers | TBC | For Fab when Confirmed | TBC | Custom fabricated — measure on site first

## Issues Log
ON-SITE ISSUES & DEFECTS LOG — 4020GA Body Installation
Issue No. | Date Found | Step / Location | Description of Issue | Severity | Action Taken / Required | Resolved? ✓ | Sign-off
001 | — | Step 4 — Bed Leveling | Racks may contain manufacturing swarf in thread holes; tap clean before fitting | Medium | Tap all mounting holes on arrival before bed leveling begins
002 | — | Step 12 — Window Install | Aluminium window strips require retapping at large diameter | Medium | Retap all strips before install; bring M5 tap and spare thread lock
Trouble with moving of exchange table