## Installation Checklist
Step | Section Title | Instructions | status | Additional Tooling Required | Materials and Consumables | Notes
1 | Foot Plates | Measurements from installation floorplan, Laser lines/string lines to align footplates, check diagonal squarness. mark for exchange table but dont install footplates |  | Laser line, String, Concrete Drill,16mm concrete drill, Battery drill, impact driver and sockets | m16 x100 screwbolt [x40], Foot plates [x20]
2 | Feet Into Body | 120mm gap between base and ground clearance for slag collection trays - Welded to footplates after machine leveled |  | Overhead Gantry/Firana hoist, large spanners, stick welder | Welding rods
3 | Connect Exchange Table Body | Connect exchange table body - Connect with threaded rod, not placed on foot plates initially - placed on roller wheels for ability to pull away for access to chain drive motor install and adjustment. rods assist with ease on alignment later. foot plates can be installed with table in location later and welded after leveling |  | Roller wheels [x4] , Lifting Equipment, Large Pry Bar, Crowbar | m16 Threaded rod [2m/0.5mx4off]
4 | Bed Leveling | Use free linear bearing & mag base dial gauge to run along rack to ensure straightness. - when unpackaging racks be careful not to remove lettering hints as the racks have mbeen drilled in place and have designated location on machine base. Bed machined surfaces will require deburring and cleaning and potentialy thread mounting holes tapped to clean swarf from manufacturing |  | Laser level with tripod and reciever, Bubble level, Deburr stone, Files, Torque wrench, Long level / straight edge, Scouring pads, Bubble levels, Dial gauge with mag base, Angle grinder with fine sanding disk, deburr knives, taps for m5,6, drill bit selection | Slideway oil, WD40, Cotton Rags
5 | Chain & Table Install | Chain, chain drive motor and chain clips installation. Install table with removed slats so we can set chain tension prior to body panels install. After chain tensioned exchange table frame can be pushed toward main body for foot plate installation and moving out exchange table for tables wheel alignment. will require forklift and straps for moving of exchange tables. |  | Hammer[Deadblow and standard], Forklift[ideally lifting boom attachment], Spanner, allenkeys and socket sets, string line, Lifting straps and shackles | Bubble level, deburr stone, slideway oil, files, torque wrench, long level / straight edge. Scouring pads, WD40, anti-seize
6 | Linear Rails & Cross Beam | Ensure linear bearing and underside of crossbeam gantry are deburred and clean before assembling - Connect oil lines tidily before placing on linear bearings. Install cross beam with bolts only finger tight to linear bearings. |  | Rags, Whetstone / Deburring tools | Included in kit
7 | Squaring Machine | Place square in centre of machine on sturdy table - leveled with packers, Mount dial gauge to laser head mounting screw holes with adapter bolt. Manually move crossbeam along Y axis to align square and clamp in position. Push gantry along X axis and adjust crossbeam with deadblow until x and y axis are 0.2mm/m straight. If awkward: continue cables and installation of required electrics before squaring of crossbeam. After squaring tighten crossbeam mounting bolts and recheck. recheck at a different location on machine. |  | Sturdy table, Packers, Dial gauge, Adapter Bolt, Square, Clamps, Torque Wrench, Deadblow | N/A
8 | Motors & Drive Gear | Install Y axis motor mount bolts at finger tight, push drive gear into racks untill fully bound with no play. Then tighten mounting bolts 30 degrees past hand tight, then do same to tension bolts so some preload is on driving gear. |  | Spanner set, socket set with extensions swivel joints | Included in kit
9 | Front Body panels and Valve Island | Install cable trays and front body panel for valve island (Extraction door numatics) connections. |  |  | Included in kit
11 | Cables and Gas Setup | Install side cable trays, oil reservoir, gas regulators, run gas lines, power lines, Potentially board with regulators/connections between site(Customer Responsibily) and Machine lines. |  | Electrical Toolkit | Oil, Gas Fittings [], Gas hoses [], Sealants/Glue []
10 | Body Panels & Wall Frame | Install front panels and rear pillar bodys without tightning mounting bolts for adjustment when installing wall panels. Install side wall framing then remove and place on layed out wall panels. drilling and taping of holes will be neccisary for proper panel alignment. after wall sections align well. remove centre wall panels for wall frame mounting bolt access and lift into location with forklift or rmanpower. Adjust front and back pillars as necessary. |  | Clamps, Drills, Laser line, Forklift, Straight edge | Large Cardboard roll or Plywood Panels for placing wall panels safely on ground. Large Clear area
12 | window install | Aluminium window strips will benifit from retapping at large diameter since manufacturing quality is low, drilling of clearence holes in machine wall panels will also be required. loosely install bottom alu rail and remove bolts on top alu rail so window glass is seated in bottom rail and top rail can be pushed in and second installer inside machine can tighten rails to hold window in place. |  | Window Suction cups, m5 Tap and 6mm Drill | Locktite
13 | Roof Install |  |  | Ladder | Included in kit
| Light Curtains/Rubber Curtains | TBC with Customer and designed as needed |  | Hole Punches, 6/8mm Concrete Drill | m6/8 Mason/Screw Bolts [x12-16], potential Light Curtain Bollard, potential Additional Rubber installed
| Extraction and Ducting | Ideally source 200dia metal ducting and draw piping route and connecting flanges for fabrication. otherwise plastic 350dia ducting attached with saddle clamps |  |  | 350Dia Hose Clamps [4x]
| Cable Protection and Wall Mounting | After Position of machine and auxilaries measure and draw for Fabrication the Floor Cable Covers |  |  | Saddle Clamps, Floor Cable Covers
Water Chiller
Voltage Reg
Control Cabnet and Systems
Air Compressor

## Additional tools
Tools | Status
Toolboxes for small parts and bolt sorting
Impact Driver assortment kit with good hex driver range (Most Used)
Taper drill bit for potential modification of alignment pins of racks
Sticker remover
1/2" to hex set
Safety Glasses
Earmuffs/EarPlugs
Gloves
Zip Ties
knee pads

## Machine Parameters
Item | Dimension | unit | notes
Control cabinet: | 1328L *700W*2138H | mm | Standalone and close to operator
Water chiller: | 750L*560W*1020H | mm | Standalone, beside control cabinet, ventilation both sides, and access both sides
Laser source: | 400L*900W *550H | mm | on rack above power regulator, close to control cabinet, available to operator
Dust collector: | 1202L*1324W*2220H | mm | can be on mezzanine but access required for filter and pulse units maintenance. Vent of air output to be considered
Power Regulator | 420 L x 680 W x 880H | mm | heavy on floor but will fit under power source
Main Machine | 10254 L x 3518 W x 2217 H | mm | allow 750mm LHS for door at operator end
allow 1000mm LHS for operator to move